## Sampling SOP
BOKITTA
Sampling SOP
PO NO
Season
Prints Theme
Prints Count
Plains Count
Action | Description
FIT SAMPLE | The fit sample is made in accordance with the specifications submitted by Bokitta and are locked for this PO. After receiving fit samples for all styles, Bokitta can approve or request remaking of fit sample after changes and comments are submitted to manufacturer. This fit samples submission can be reiterated several times before Bokitta approval.
PhotoShoot Samples | When manufacturer receives strike offs of prints or dyed fabric, photoshoot samples for each print and each plain color and in all ordered styles must be sent to Bokitta for photoshoot.
PRE-PRODUCTION/SEALER SAMPLE | It is done for the VoiulaMaxi size only of any one color and actual fabric and actual trims are used. Must be submitted before actual production and must get approval before production starts.
Style -SET SAMPLES | These production samples are made in actual fabric and trims in all sizes and is sent to the buyer for reference.
Supplier Authorized Signatory and company seal
I Confirm acceptance of this purchase order and all of its tems and conditions as stated by this PO in all its pages. The acceptance of this PO presupposes that you are in agreement with all its specific conditions.

## Planner
BOKITTA
PO Planner
PO NO
Season
Prints Theme
Prints Count
Plains Count
Step | Phase | Action | Responsible Party | Delegated to | Planned Date | Delay Date | Actual Date | Comments
1 | Pre Order | Purchase Order placed, initial quanity specified | Bokitta
2 |  | Required DELIVERY date to Forwarder | Bokitta
3 |  | Acceptance of DELIVERY to Forwarder | Manufacturer
4 |  | Acceptance of Purchase Order Terms and conditions as per worksheet | Manufacturer
5 |  | Submission of Artworks and accessories specification by Bokitta team | Bokitta |  |  |  |  | BOM sheet in PO worksheet has all links to artworks
6 |  | Approval of artworks, patterns and sewing guides | Manufacturer
7 |  | Submission of FIT Sample for each style and size | Manufacturer
8 |  | APPROVAL of FIT Sample for each style and size | Bokitta | Mohammad
9 |  | Strike off/Lab dips Submission for all fabrics toghether | Manufacturer |  |  |  |  | Must match with PO 2 colors
10 |  | APPROVAL of S/O L/D For all fabrics | Bokitta | Hala
11 | Processing | Quantities and specification locked | Bokitta | Wafa
12 |  | Confirmation of Purchase Order by supplier, Signature | Manufacturer
13 |  | Advance Payment | Bokitta
14 |  | Submission of all trims, packing material | Manufacturer
15 |  | Approval of all trims, packing material | Bokitta | Wafa
16 |  | PHOTOSHOOT SUBMISSION using S/O fabrics | Manufacturer |  |  |  |  | if not possible using S/O fabric then FOB fabric
17 |  | SUBMISSION of all Fabric FOB used in product | Manufacturer |  |  |  |  | All fabrics must be submitted toghther; shell, lining and jersey
18 |  | Approval of all Fabric FOB used in product | Bokitta | Wafa
19 |  | PHOTOSHOOT SUBMISSION using FOB fabrics | Manufacturer |  |  |  |  | if not possible to use S/O fabric then FOB fabric
20 | SEAL | SUBMISSION of Sealer Sample for each style and size | Manufacturer
21 |  | APPROVAL of Sealer Samples | Bokitta | Wafa |  |  |  | check Sampling SOP
| PCD | Cutting start | Manufacturer
22 | Production | Submission of COMPLETE PP Samples for all styles and all prints | Manufacturer
23 |  | Approval of PP Samples submission for all styles and all prints | Bokitta | Wafa
|  | Production Starts | Manufacturer
| Delivery | Submission of Final Inspection and Carton Count Reports | Manufacturer
24 |  | Approval of Final Inspection Report and authorization to deliver | Bokitta | Mohammad
|  | 1st DELIVERY of PO Goods to Forwarder | Manufacturer
|  | 2nd DELIVERY of PO Goods to Forwarder | Manufacturer
|  | 3rd DELIVERY of PO Goods to Forwarder | Manufacturer
1 |  | Pre Order phase - Specifications and quantity can change
2 |  | Processing Phase - All specifications and quantities are frozen
Supplier Authorized Signatory and company seal
I Confirm acceptance of this purchase order and all of its tems and conditions as stated by this PO in all its pages. The acceptance of this PO presupposes that you are in agreement with all its specific conditions.

## Inspection SOP
BOKITTA
Inspections SOP
PO NO
Season
Prints Theme
Prints Count
Plains Count
Report No. | Report Description | Responsible Manager | Delegated to | Report Intended Date | Submission Date | Comments
SHADE SEGREGATION REPORT
100% CUT COMPONENT QUALITY CHECK REPORT
Spreading
LAY RECORD
FINISHING ONLINE QUALITY AUDIT REPORT
NEEDLE DETECTION RECORD
NEEDLE DETECTOR CALIBRATION LOG
BROKEN NEEDLE RECORD
PIECE GOODS INSPECTION REPORT
FINISHING INTERNAL CARTON AUDITING REPORT
MEASUREMENT INSPECTION REPORT
TRIMS INSPECTION REPORT {LABELS, HANGTAGS, ELASTIC AND THREADS}
CUTTING INSPECTION REPORT
100% INLINE INSPECTION REPORT
FINAL AUDIT REPORT
FINAL INSPECTION REPORT
Supplier Authorized Signatory and company seal
I Confirm acceptance of this purchase order and all of its tems and conditions as stated by this PO in all its pages. The acceptance of this PO presupposes that you are in agreement with all its specific conditions.